## Sheet1
AM62x SKEVM - Changes Required for E2 release
AM62x Sub Section | Changes to be made on AM62x SKEVM SCH Rev - E1 | Reason for changes | Changes to be made on AM62x SKEVM BOM Rev - E1 | Changes to be made on AM62x SKEVM Layout Rev - E1 | TI Comments | Status
PD Controller | Replace Resistor R470 with 10K | PD Controller should be configured to operate in BP_Nowait and Safe configuration. So ADCIN1 pin of PD controller should be strapped with voltage divider 10K and 100K. | 1Nos Resistor (R470) with part number RC0201JR-0710KL to be used |  |  | Closed
PD Controller | Resistors R158 and R164 should be made DNI. Resistors R157 and R163 should be mounted with 0E. | I2C1 instance (Master or Slave capable) of PD controller should be routed to the Aardvark Header J22 pins 1 and 3 instead of I2C3 instance. | Resistors R158 and R164 will be made DNI. Resistors R157 and R163 should be mounted with 0E Resistor Part# RC0201JR-070RL. |  |  | Closed
SoC CLK | C322 and R368 should be made DNI | Voltage drop(1.2V instead of 1.8V) observed on clock signal SoC_CLKIN of SoC. | C322 and R368 - to be made DNI |  |  | Closed
UART - SoC_UART1 | R431 should be made DNI and R176 should be mounted with 10K | SoC_UART1 signals to be connected to FT4232 by default instead of User EXP HDR. | R431 - to be made DNI R176 - should be mounted with 10K Part# RC0201JR-0710KL. |  |  | Closed
Boot mode | Pull up should be provided on WL_LT_EN signal. R11 should be made a pull up resistor and it should be pulled up to VCC_3V3_SYS | Incorrect logic levels seen on Bootmode pins of SoC because the buffer U3 is enabled by default. So this buffer should be disabled(EN pulled high) by default and can be enabled through IO Expander. |  | R11 will be a pull up resistor on WL_LT_EN signal connected to VCC_3V3_SYS |  | Closed
Boot mode | Pull up should be provided on AUD_BUF_EN signal. R459 should be made a pull up resistor and it should be pulled up to VCC_3V3_SYS | Incorrect logic levels seen on Bootmode pins of SoC because the buffers U64 and U65(McASP2 Buffers) are enabled by default. So these buffers should be disabled(EN pulled high) by default and can be enabled through IO Expander. |  | R459 will be a pull up resistor on AUD_BUF_EN signal connected to VCC_3V3_SYS |  | Closed
Boot mode buffers | R221 will be made DNI and R222 will be mounted with 0E resistor | RESETSTATz will be connected to SYSBOOT_BUF_ENz instead of PORz_OUT through 0E resistor option. | R221 - Made DNI R222 - Resistor 0E with part number CRCW04020000Z0ED to be used |  |  | Closed
Boot mode Switches | Boot mode signals connections to SW1 and SW2 will be changed according to the Switch numbers for easier access |  |  | Boot mode Switches SW1 and SW2 should be placed straight for easier User accessibility |  | Closed
Q13 FET | Replace Q13(CSD13383F4) FET with a bigger package FET(CSD16301Q2) | Because of the small size and LGA package style of CSD13383F4, we are facing Assembly issues | Q13 to be changed to CSD16301Q2 |  |  | Closed
Q1, Q3, Q4, Q5, Q6, Q7, Q8 and Q9 FETs | Replace these FETs(CSD13383F4) with a bigger package FET(CSD16301Q2) | Because of the small size and LGA package style of CSD13383F4, we are facing Assembly issues | Q4, Q5, Q6, Q7, Q8 and Q9 to be changed to CSD16301Q2 |  |  | Closed
USB | SoC_USB0 instance will be connected to Type-C Connector J13 | Customer change request | NA | SoC_USB0 instance will be connected to Type-C Connector J13 |  | Closed
HDMI | Data mapping to be changed to RGB 5:6:5 instead of YC 4:2:2 | Customer change request | NA | Data mapping to be changed to RGB 5:6:5 instead of YC 4:2:2 |  | Closed
HDRs alignment | J9 and J10 Headers should be aligned as other SK platforms | This needs to be corrected which was missed out in E1 Rev. |  | J9 and J10 Headers should be aligned as other SK platforms |  | Closed
USB HUB | SoC_USB1 instance will be connected to USB 2.0 HUB or Directly to Micro AB Connector? TBD 1/27: USB Hub Removed and connected USB1 instance directly to Type-A Port | 1/27: As per TI Review Comment received by Email on 1/25 | 1/27: Changed J7 connector to 629104151021 | 1/27:Update USB Connector to Single Type-A 2/2: Load switch used to enable the 5V0 supply to Type-A port is always, a pull up resistor is provided on the EN signal. |  | Closed
Ethernet PHY | 1/27: Clock Skew changes to be finalized 2/2: Separate IO EXP GPIOs are used to RESET the PHYs individually 2/8: Awaiting changes required in this section, Need confirmation to proceed for fabrication 2/10: On Ethernet PHYs VDDA1P8 nets which are currently shorted to be removed as PHY team recommended that pins 13 and 48 should not be tied on the PHYs when that supply isn’t used. Hence given one of these pins on test points and on as no connect for space constrainsts 2/21: Changes made on schematics as per review comments received. Changes made on layout as per comments shared. | 2/2: Using the same architecture as E1 2/10: As per customer change request by Email dated 2/10 2/21: AS per Review comments received over Email dated 2/21 |  | 2/10 : Nets connected togeter on pins 13 and 48 on PHY ic's isolated 2/17: Necessary layout updates on ETH MDC/MDIO lines 2/21: Implement changes in schematics and impletement below review comments on layout: 1) Try to avoid copper below the RJ45 between the shield connections and the MDI signals. 2) clearance between the earth and the circuit ground DGND (provide 40 mil) 3) 2X spacing between MDI signals and other traces including GND 4) GND pour to cover the entire pins of the RJ45 connector | 2/17: Need to route MDC/MDIO with a 3 point connection as suggested in the Email, Also would need to avoid crossing voids wherever possible 2/21: Test points to be provided for both VDDA1P8 pins, Rbais resistor to be changed to 10K in both PHY chips, Add additional 2.2K pull-up on INTn line near U49 chip, test points to be added on XO pin of both PHY chips. | Open
Wilink | WLAN_EN connected through I2C IO Expander instead of GPIO0_71 (MM2_SDCD) 1/27: Provided Option for MMC2_SDCD to provide EN signal to WiLink Module, Default option for EN to WiLink module will be from I2C IO Expander. Added Pull-down resistor on MMC2_SDCD pin 1/28 : Wilink Section needs to be tested by software team before we release for fabrication 2/8: Removed option for WLAN_EN from IO Expander, using only MMC2_SDCD pin for WiLink EN. This is done for freeing up IO for Interrupt as per E-mail sent on 2/7 Need confirmation to proceed for fabrication 2/21: Added pull-down resistor on MCASP1_AXR0_BT line | 1/27: As per TI Review Comment received by Email on 1/27 2/8: Updated free up IO for dedicated GPIO for MCU Header and separate IO for Interrupt 2/21: As per suggestion given by TI | 1/27 : Added Resistors R652 0E (R651 will be DNI by default) Added resistor R626 10K (For MMC2_SDCD pull-down) Added level translator - SN74AVC2T244DQMR (U98 ) for 3.3V to 1.8V conversion for WL_EN signal from IO Expander 2/8: Removed 0E resistor R652 and pull-down resistor R626 2/21: Pull-down of 100K added | Used GPIO port Expander GPIO P01 as WLAN_EN 1/27 : Route WLAN_EN signal from IO Expander and SoC 2/8: Layout updates in IO Expander and SoC GPIO section 2/21: Layout updated with pull-down resistor |  | Open
Buck Boost Controller | We will be replacing LM34936 Buck boost controller with a Buck boost converter TPS630701 | To overcome issues overserved with LM34936 in VIN voltages of 9V ,12V & 15V |  | We will be replacing LM34936 Buck boost controller with a Buck boost converter TPS630701. |  | Closed
LEDs for 3V3 and VDDR_CORE voltage rail | Power indication LEDs are provided for VCC_3V3_SYS and VDDR_CORE . | For easier user confirmation on the presence of important voltage rails |  | Power indication LEDs are provided for VCC_3V3_SYS and VDDR_CORE voltage rails for easier user confirmation on the presence of important voltage rails |  | Closed
McASP2 Buffers | Removed U64 and U61 2/2 : No longer valid , since McASP2 is now used for 24-Bit DSS | Unused signal channel of U65 and U60 is used for MCASP2_AXR3_AUD and MCASP2_AXR3_WL signals 2/2: MUX + Switch used on McASP1 Instead to support IO's for 24-Bit DSS |  | Removed U64 and U61 Buffers 2/2: Re-Route based on new connection |  | Closed
LVDS Display Connector | Rotating the Display Connector orientation by 180' to match the current mounting orientation | Because of the wrong assembly done in the E1 version |  | Rotating the Display Connector orientation by 180' to match the current mounting orientation |  | Closed
IO Expander | 1/27 : IO_EXP_INTn not going low when triggered, Need to test this and implement necessary changes -TBD 1/28 : R550 resistor changed to 4.7K | 1/28: Since The Schmitt Trigger buffer U46 is driving high always and the IO expander is unable to sink the current an series resistor is added on the path | Change R550 to 4.7K |  |  | Closed
Audio | 1/28: The audio codec needs to be tested with Bare Metal diagnostics before we release the board for fabrication 2/8 : No updates yet, Need confirmation to proceed for fabrication 2/21: Audio Codec tested with Bare Metal test code, no changes required on Hardware | 1/28: Since there are issue's with Linux Driver, we would need to test this interface with Bare Metal Driver |  |  |  | Closed
CSI Display | 1/28: The CSI camera to be tested before we release the board for fabrication 2/8 : Suggested to add stronger pull-up on I2C line going to CSI connector, Awaiting confirmation 2/21: I2C-2 to connect to CSI header via I2C Buffer, Pull-up value for this yet to be finalized |  |  |  |  | Open
HDMI | 2/2: 24 Bit DSS instead of 16 Bit for HDMI transmitter, To Support this, the following changes are required: 1) UART1 and McASP2 signals are now routed to HDMI transmitter which were earlier routed to Audio Codec & BL Audio 2) McASP1 gets muxed between HDMI, Audio Codec and BL Audio, this is achieved by using a MUX and Buffer. Control to the MUX is by Jumper and EN to the MUX and Buffer is from IO Expander 3) Linux Console UART0 loses Hardware Flow Control. The UART0_CTSN connected to EXP connector as GPIO1_22 and UART0_RTSN is used for UART1 FET SEL. ( To use the UART0_CTSn as GPIO_22 and to replace GPIO_32 which is now used for MCASP1_AXR2) 4) UART1 gets muxed 3 ways, FT4232, Pi Hat for SPI or Wilink Bluetooth. This is achieved by using a MUX and Buffer. Control to the MUX is by Soc pin UART0_RTSn and EN Buffer is from IO Expander 2/8: Need confirmation to proceed for fabrication | 2/2: Customer change request | NA |  |  | Open
SoC_UART0 | 2/2: Removed the flow control signals of SoC_UART0 instance to FT4232. Using the UART0_CTSN for EXP connector as GPIO1_22. Using the UART0_RTSN as UART1_FET_SEL | 2/2: To use the UART0_CTSn as GPIO_22 and to replace GPIO_32 which is now used for MCASP1_AXR2 |  |  |  | Open
McASP1 | 2/2: Using GPMC0_ADVN_ALE as MCASP1_AXR2 audio channel. MCASP1 will be shared b/w HDMI, Audio codec and BT through a FET Switch(b/w HDMI and Codec) and Level Translator buffer(WLAN BT). These FET Switch and Buffer has individual enable signals for IO EXP. Jumper is provided for SEL signal of FET Switch to route MCASP1 to either HDMI or Codec. The same signal is also connected to one of the GPIOs of IO EXP for SoC to read the current routing of MCASP1. 2/8 : McASP1 signals from MUX should be connected to the Codec by Default | 2/2: Customer change request 2/8 : As per customer change request over email dated 2/3 | FET Switch SN74CB3Q3257PWR , Buffer TXB0104RUTR and the associated discrete components will be added |  |  | Open
UART - SoC_UART1 | 2/2 : SoC_UART1 which was earlier shared between EXP conn and FT4232 through a FET Switch is also routed to BT_UART through a level translator Buffer. Common Enable signal from IO EXP( and its inverted signal) is used to enable the FET Switch and the buffer. Select signal of the FET Switch(B/w EXP and FT4232) has resistor stuffing options and it is also routed to SoC GPIO (UART0_RTSN) 2/8 : UART1_FET_BUF_EN routed to IO Expander and SoC GPIO1_23 Used for Interrupt instead 2/17: UART1 MUX ouput to be routed to FT4232 by default | 2/8 : As per customer change request over email dated 2/3 2/17: As per customer change request over email dated 2/10 |  |  |  | Open
MCU Header | 2/8 : MCU_GPIO0_15 to be connected from SoC to MCU header directly and not used for Interrupt. GPIO1_22 to be used for Interrupt which is connected to Switch and IO expander interrupt | 2/8 : As per customer change request over email dated 2/3 |  |  |  | Open
I2C | 2/17: Remove CSI Header from I2C1. Use I2C2 instance and connect to an I2C buffer TCA9543, the output of this buffer would connect to CSI Header and the expansion header | 2/17: Customer change request as per email dated 2/11 |  |  |  | Open
Power Sequencing | 2/12: Based on power sequencing scope captures 3 issues were identified: 1) The 3V3 seemed to have some reverse current. 2) Glitch on MCU_PORz 3) VDD_CORE and VDDR_CORE ramp down sequence issue Tests were conducted to find the root cause 1) There wasn't any issue observed while probing the 3.3V rail, hence no change in desingn 2) Glitch was because PG of the VDDR LDO was pulled up to 3.3V whereas VIN was 1.8V, changeing the pullup to 1.8V resolved the issue 3) To ensure VDDR_CORE comes down before VDD_CORE, TI Suggested replaceing the VDDR_CORE LDO with TPS62824 and adding an OR gate with an RC delay circuit at the output of the OR gate. 2/18: Necessary changes were made on the schematics based on suggestions given by TI | 2/12 : Changes to be made as per issues observed in the power sequencing |  |  |  | Open
TPS6282x section | 2/21: Changes made on schematics as per review comments received. Layout updates done accordingly | 2/21: As per review comments received over Email dated 2/21 |  | 2/21: Layout updates done as per review comments | 2/21: move the passives C110, L15 and C107 of U32. Feed back path to be kept closer to the generation point to reduce inductance, same to be done for VDD_CORE generator as well | Open
INA Current Sensor | 2/21: U16 pin A0 & A1 connected to VCC_3V3_SYS | 2/21: As per review comments received over Email dated 2/19 |  | 2/21: Layout updates done as per review comments | 2/21: Change the INA231 Address pins on device that currently has Address 0X4B to be both pulled up to Vs so resulting address 0x45 | Open